## Projektplaner
Scrabble 13
[5 empty] | Selected Time: | 71 |  |  | Duration of Activity |  |  |  | Actual Duration |  |  |  | % completed |  |  |  | Delay |  |  | % completed (delayed)
Activity | START | DURATION | ACTUAL START | ACTUAL DURATION | PERCENTAGE COMPLETED | Timeline | time axis 2021-03-18 to 2021-05-31
[6 empty] | 1 | 2 | time axis 2021-03-18 to 2021-05-31
Maven Setup | 1 | 2 | 1 | 1 | 100%
Project Structure | 1 | 1 | 1 | 1 | 100%
Network Connection | 21 | 7 | 23 | 9 | 100%
Messages | 29 | 7 | 32 | 29 | 100%
Protocol Server | 37 | 14 | 38 | 18 | 100%
Protocol Client | 38 | 14 | 38 | 18 | 100%
Game Build (components) | 6 | 5 | 6 | 5 | 100%
Scoreboard | 6 | 1 | #VALUE! | - | -
Game Flow | 11 | 7 | 11 | 6 | 100%
Player classes | 18 | 5 | 18 | 8 | 100%
Import Dictionary | 9 | 8 | 9 | 19 | 100%
Board Placement Check | 23 | 7 | 29 | 7 | 100%
Score Evaluation | 31 | 10 | 31 | 15 | 100%
Game Results (Statistics) | 41 | 5 | 66 | 5 | 100%
Update Player Profile Info | 47 | 3 | 47 | 1 | 100%
Tutorial | 56 | 12 | 71 | 5 | 100%
Player Profile <-> XML | 6 | 9 | 6 | 21 | 100%
XML-Parser (BoardState, PlayerInfo) | 32 | 8 | 32 | - | -
Game History (SQL) | 66 | 5 | #VALUE! | - | -
Menu GUIs | 6 | 30 | 9 | 0 | 100%
Game GUI | 37 | 30 | 0 | 0 | 100%
Sounds | 61 | 7 | 0 | 0 | 100%

## Project History
checked
| Use Cases |  |  | User Interface Mockups
| 1 | Manage Player Profiles |  | Main Screen |  | Tools
| 2 | Play Scrabble |  | Player Profile Manager |  | Figma
| 3 | Play Network Game |  | Game Lobby |  | Draw.io
| 3.1 | Host Game |  | Game
| 3.2 | Join Game |  | Tutorial
| 3.3 | Chat
| 3.4 | Leave Game
| 4 | Play Tutorial
| 5 | Display Statistics
| Functional Requirements |  |  | Domain Models
| 1 | Cover entire rulebook
| 2 | At least two AI players
| 3 | Game session stats & leaderboard |  |  |  | Third-Party Libraries
| 4 | In-Game stats & leaderboard |  |  |  | JavaFX
| 5 | Game Customization (Dict & LS/LD) |  |  |  | Maven
Architecture Diagram
| Operation Contracts |  |  | System Sequence Diagrams
| 1 | Manage Player Profiles |  | 1
| 2 | Play Scrabble | Yilmaz | 2 | Yilmaz
| 3 | Network | Yasin | 3 | Yasin
| 4 | Tutorial | Vincent | 4 | Vincent
| 5 | Display Statistics | Valentin | 5 | Valentin

## Tasks
Tasks | Start Plan Date | Plan Duration | End Date | Actual Start Date | Actual Duration | Actual End Date | Completion | Delay | Assigned |  | #VALUE!
Maven Setup | 2021-03-16 | 2 | 2021-03-18 | 2021-03-16 | 1 | 2021-03-17 | 100% | 0 | Team
Project Structure | 2021-03-18 | 1 | 2021-03-19 | 2021-03-16 | 1 | 2021-03-17 | 100% | 0 | Team
Network Connection | 2021-04-05 | 7 | 2021-04-12 | 2021-04-07 | 9 | 2021-04-16 | 100% | 4 | Yasin, Valentin
Messages | 2021-04-13 | 7 | 2021-04-20 | 2021-04-16 | 29 | 2021-05-15 | 100% | 25 | Yasin, Valentin
Protocol Server | 2021-04-21 | 14 | 2021-05-05 | 2021-04-22 | 18 | 2021-05-10 | 100% | 5 | Yasin, Valentin
Protocol Client | 2021-05-05 | 14 | 2021-05-19 | 2021-04-22 | 18 | 2021-05-10 | 100% | 0 | Yasin, Valentin
Game Build (components) | 2021-03-21 | 5 | 2021-03-26 | 2021-03-21 | 5 | 2021-03-26 | 100% | 0 | Yilmaz
Scoreboard | 2021-03-21 | 1 | 2021-03-22 | - | - | - | - | - | -
Game Flow | 2021-03-26 | 7 | 2021-04-02 | 2021-03-26 | 6 | 2021-04-01 | 100% | 0 | Yilmaz
Player classes | 2021-04-02 | 5 | 2021-04-07 | 2021-04-02 | 8 | 2021-04-10 | 100% | 3 | Yasin, Yilmaz
Import Dictionary | 2021-03-24 | 8 | 2021-04-01 | 2021-03-24 | 19 | 2021-04-12 | 100% | 11 | Valentin
Board Placement Check | 2021-04-07 | 7 | 2021-04-14 | 2021-04-13 | 7 | 2021-04-20 | 100% | 6 | Yilmaz
Score Evaluation | 2021-04-15 | 10 | 2021-04-25 | 2021-04-15 | 15 | 2021-04-30 | 100% | 5 | Yilmaz
Game Results (Statistics) | 2021-04-25 | 5 | 2021-04-30 | 2021-05-20 | 5 | 2021-05-25 | 100% | 25 | Vincent
Update Player Profile Info | 2021-05-01 | 3 | 2021-05-04 | 2021-05-01 | 1 | 2021-05-02 | 100% | 0 | Nico
Tutorial | 2021-05-10 | 12 | 2021-05-22 | 2021-05-25 | 5 | 2021-05-30 | 100% | 8 | Vincent
Player Profile <-> XML | 2021-03-21 | 9 | 2021-03-30 | 2021-03-21 | 21 | 2021-04-11 | 100% | 12 | Nico
XML-Parser (BoardState, PlayerInfo) | 2021-04-16 | 8 | 2021-04-24 | 2021-04-16 | - | - | - | - | -
Game History (SQL) | 2021-05-20 | 5 | 2021-05-25 | - | - | - | - | - | - | In Development
Menu GUIs | 2021-03-21 | 30 | 2021-04-20 | 2021-03-24 |  |  | 100% |  | Max, Vincent | Critical
Game GUI | 2021-04-21 | 30 | 2021-05-21 |  |  |  | 100% |  | Max | implemeneted, pending tests
Sounds | 2021-05-15 | 7 | 2021-05-22 |  |  |  | 100% |  | Nico | done ( incl. Tests)
[5 empty] | 0 |  |  |  |  | fell away (not required)
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0